## Deployment plan
PROJECT IDENTIFICATION
HOST | VENDOR
Company Securities Corporation | Navisoft
Project Started | Product Launch Date
Project Manager | Team Lead
Nguyễn Nhật Linh
DEPLOYMENT IDENTIFICATION
PREPARED BY | Navisoft
UPDATED ON | 22/07/2024
SYSTEM | Super Core
RELEASE VERSION | v1.1.722.1
COMPONENT(S) | [X] HNXTPRLGate
[ ] DATABASE
[ ] OTHER:_____________________
DEPLOYMENT OVERVIEW
AFFECTED SERVERS | [X] SIT
[ ] UAT
[ ] PROD (MAIN)
[ ] OTHER:_____________________
UPDATE TYPE | [X] FUNCTIONAL
[ ] BUG FIX
[ ] RULES
[ ] DATABASE
[ ] OTHER:
DEPLOYMENT METHOD | [X] FULL IMAGE
[ ] PARTIAL IMAGE
[ ] OTHER:_____________________
TARGET | SIT: 22/07/2024
IMPLEMENTATION DATE
UPDATE DESCRIPTION
Change of Application:
- Detail of changes: HNXTPRLGate: 1. Bổ sung thêm config bật tắt Kafka, DB 2. Fix lỗi gửi side khi nhận được message EE trả về RE
Change of Database:
Patch SQL:
Change of Configuration or evironment variables:
<không thay đổi>
Change of Server
LIST OF CHANGES
- Deployment files
- Library code:
BINARY FILES
HNXTPRLGate
All file.dll
Note on B27: Linh.Nguyen:

## Scripts
Server | Area | Account | Script | Directory | Last Updated in Server

## SIT (root)
Environment | Sequence | Section | Task | Directory | Command | Backup Location | Description | Success | Failure
SIT | 1 | HNXTPRLGate | Stop service
| 2 | HNXTPRLGate | Bổ sung config "KafkaConfig": {"EnableKafka": true} và "EnableSaveDB": true |  |  |  | - "EnableKafka": false tắt sử dụng kafka '- "EnableKafka": true bật sử dụng kafka '- "EnableSaveDB": false tắt sử dụng ghi Database '- "EnableSaveDB": true bật sử dụng ghi Database
SIT | 2 | HNXTPRLGate | DeploymentApp |  |  |  |  | Ứng dụng HNXTPRLGate run version 1.1.722.1

## PROD (root)
Environment | Sequence | Section | Task | Directory | Command | Backup Location | Description | Success | Failure